HMICFRS Handling of Misconduct Improvement Plan
No.	Recommendation	Current Service RAG status	Identified Area(s) for improvement / enhancement	Owner	Due Date	Status of improvement objective	Comments
1	By 1 February 2025, chief fire officers should, as a priority, make sure their staff are aware of, and follow the Core Code of Ethics. Services should build the code into all relevant policies and practices.						No areas of improvement identified. The CCoE will be reviewed in line with normal reviewed timeframes.
2	By 1 February 2025, chief fire officers should make sure a policy for probationary staff is in place. This policy should make clear that services can immediately dismiss probationers who fail to meet the required standards of behaviour set out in the Core Code of Ethics and the Code of Ethics fire standard		To review procedures to formalise processes for FF apprentices as per organisational learning action	HoPOD / HoT	Feb 25		The Service have set processes in place for probation which include behaviour. / Nov Update: A specific process for apprentices is being developed. / Feb Update: The probationary procedure has been updated to reflect these changes
3	By 1 May 2025, chief fire officers should make sure their workforce plans allow staff to be moved from a wholetime watch to a different watch or station, within their contractual requirements, proactively and reactively as required. / By 1 May 2025, chief fire officers should also make sure firefighters who are promoted are posted to a different watch or station, including when the promotion is temporary for two months or more. If this isn’t possible, chief fire officers should show how the risks of reinforcing a negative culture have been addressed		To review the Promotion and Transfer procedures to incorporate the necessity to move watch when promoted.	DPOD	May 25		The Service does do this already however, it is not documented formally in the procedure or in the SWP. / Feb Update: Both documents have been updated
			To include in the SWP	DPOD	May 25		Nov update: The SWP has been updated and agreed by SLT
4	By 1 February 2025, chief fire officers should make sure their services create or have access to dedicated professional standards function to oversee the investigation of concerns raised within a service or from an external source. This should oversee cases to make sure they are investigated in a fair and transparent way, manage complex cases directly and act as a point of contact for all staff involved.		Identify ways this could be facilitated and present options to SLT for final decision.	HoPOD	Feb 25		Nov update: A report was presented to SLT on 29 October and a subsequent report will be presented at HRC for final approval of options. / Feb update: Discussion have progressed with Durham Police and are ongoing. / A regional MOU has been drafted for support across all NE services which will be discussed and progressed at the February meeting.
5	By 1 November 2024, chief fire officers should make sure all staff understand how to raise a concern and use grievance and whistle-blowing processes. Chief fire officers should: / make sure staff know how services will handle responses and maintain confidentiality and anonymity; and / explain how staff can access services’ whistle-blowing capability and the difference between whistle-blowing and other processes for raising concerns.		To develop a short animation and written document to outline the difference in processes which can be used to ensure all staff are aware of how to raise concern and the most appropriate method (potentially liked to QR code).	DPOD / HoC	Nov 24		Nov update: There is a delay in progressing this option due to a vacancy for a graphic designer. The work however has been logged once this position is in place. / Feb Update: The document and animation are nearly complete.
			Ensure the video is used as part of onboarding for new staff.	DPOD / TODM	Mar 25
			Work with relevant unions to ensure their representative are clear on Service processes so they can appropriately advise.	DCFO / DPOD	Nov 24		February update: Discussion with relevant unions has been progressed regarding this and updates to the revised policy agreed.
6	By 1 February 2025, chief fire officers should make sure a programme of training is in place for all supervisors and managers on how to manage staff performance and welfare and how to raise an issue. It should be supported by relevant policies and procedures. Training should include: / staff welfare and absence management. / the process for managing individual staff performance, addressing poor performance and potential misconduct issues. / how to handle difficult conversations and resolve issues informally, if appropriate, when a concern is identified; and / clarifying the role of HR services in helping managers to deal with staff concerns and misconduct issues. / Chief fire officers should make sure all managers and supervisors attend the training programme.		Identify proportion of managers who have undertaken the leadership courses and consider ways to ensure all managers have had the relevant input prior to the 1 February 2025.	TODM	Feb 25		Nov update: The service has identified a range of ACAS e-learning modules which cover discipline & grievance, bullying and harassment and undertaking investigations. All managers in the service will be required to complete these modules to ensure a level of core basic learning. Certificate will be held on file. Modules must be complete prior to the end of February 2025. / Other CPD and learning opportunities are being identified to support the e-learning modules. / February update: Communication has been sent to all line managers regarding this requirement. The deadline has been set for 31 March 25.
7	By 1 May 2025, chief fire officers should make sure the policies and processes for misconduct are consistent for all staff and are fairly applied within their respective conditions of employment.						All service policies and procedures are the same for all staff groups
8	By 1 November 2024, chief fire officers should make sure all allegations of misconduct are handled in a consistent way and staff have confidence in misconduct processes. Chief fire officers should carry out a full review of the processes, from initial identification of a misconduct issue through to the resolution or outcome. This should include a review of how services: / monitor and manage investigations. / maintain accurate records; and / adhere to required timescales.		Arrange an internal audit with DCC on the disciplinary process and recommendations for improvement.	DPOD	Nov 24		Nov update: The audit is scheduled to take place in October. Any actions identified will be added to the action plan. / The audit was undertaken in October with the initial findings giving a substantial rating. Some areas for improvement were identified and have been added to the internal audit action plan. A number of these were already noted in this plan. / February update: All actions identified are complete and the plan is signed off.
9	By 1 August 2025, chief fire officers should introduce a case management system if they don’t already have one. The case management system should allow data to be produced that will help them to better understand and oversee misconduct cases in their services.		To update the current spreadsheet to include diversity data and timescales to allow data to be produced. This will be included in the ER update to SLT and HRC.	HoPOD	Oct 24		Nov update: The Service has a case management system in place via an Excel Spreadsheet which allows for tracking and monitoring. The internal audit also highlight some additional fields for inclusion to enhance the data recorded such as suspension dates and nominated people for welfare. This has been actioned.
			To explore and identify case management systems and associated costs to consider feasibility (MS 365 / PowerBi).	HoPOD	May 25
10	By 1 May 2025, chief fire officers should make sure their services have enough capacity to carry out their misconduct investigations. They should consider using external investigators or a similar independent resource to support the process if required.		To evaluate the timescales taken for each investigation and understand the barriers for decreasing these times.	HoPOD	Dec 24		February Update: the work regarding timescales is still ongoing however, it is expected progress will be made by the end of February.
			To make recommendations based on the outcome of the evaluation.	HoPOD	May 25
11	By 1 May 2025, chief fire officers should review the training their services provide for supervisors and managers who investigate misconduct issues at all levels. Chief fire officers should make sure: / all staff who carry out investigations receive adequate training to carry out the task. / a programme of refresher training and ongoing support is available so that staff can maintain a level of competence; and / it is clear how services’ HR provision, staff associations and any trade union representative or fellow employee will support the investigation process.		To create an annual CPD package for all managers who are able to undertake investigations, hearings or appeals based on organisational learning	HoPOD	May 25		February Update: A package is currently being developed and the training given as part of leadership programmes updated. / February update: The relevant procedures have been reviewed and deemed clear and suitable.
			Review all relevant procedures to ensure HR and representative bodies support is clear	HoPOD	May 25
12	With immediate effect, chief fire officers should make sure all staff are aware of the welfare support, including occupational health support, which is available to staff involved in misconduct processes. Chief fire officers should encourage all staff involved in misconduct processes to access this support, whether they are an alleged perpetrator, complainant, witness, investigator, or decision-maker. / Welfare personnel should be independent of the investigation and have been appropriately trained for this role.		To ensure the role of a Welfare Officer is covered in any CPD.	HoPOD	May 25		February Update: The training being developed covers the role of the welfare officer.
			To include the welfare officers’ responsibilities in the Discipline Policy so they are clear.	HoPOD	Oct 24		Nov update: This has been added to the Policy and is currently out for consultation. / February update: the policy and procedure have been published.
			To send written guidance to the nominated welfare officer at the time of appointment.	HoPOD	Oct 24		Nov update: A document has been created and is being sent
			To ensure welfare is offered to all parties not just the alleged perpetrator and information is logged in the spreadsheet.	HoPOD	Oct 24		Nov update: This is now in place for all parties involved
13	By 1 November 2024, fire and rescue authorities and chief fire officers should consider varying the approach to hearing appeals so that appeals for complex or serious cases are heard by a panel rather than one person. / By 1 February 2025, FRA’s and chief fire officers should make sure all service managers and members of fire and rescue authorities who hear appeals receive appropriate training. Chief fire officers should make sure services have a consistent approach to hearing appeals.		Discuss with Clerk arrangements to provide training to appeal panel	DPOD	Nov 24		Nov update: Appeal training has been arranged for January 2025 / February update: the date for this training was moved to February.
			Consider options for appeal training for all appropriate managers	DPOD	Feb 25		Nov update: Appeal training for officers has been arranged for January 2025 / February update: the date for this training was moved to March.
14	By 1 November 2025, chief fire officers should implement a process that makes sure they can oversee and scrutinise their services’ performance relating to misconduct issues. This process should provide: / a strategic overview of performance and analysis of trends, including disproportionality. / regular reporting of issues, outcomes, and trends to the FRA; and / identification of learning outcomes and how they will be shared with fire and rescue service staff, to prevent repeat behaviours.						A report a produced for both SLT and HRC on a quarterly basis which includes relevant information.
15	By 1 February 2025, chief fire officers should put in place a process for sharing learning from misconduct cases that have been resolved while preserving the confidentiality of all parties involved. Any learning should feed into the national system, when established. / By 1 May 2025, the NFCC should establish a system for sharing learning from more serious cases of misconduct with fire and rescue service staff. The information shared should preserve the anonymity and confidentiality of all parties involved. The College of Fire and Rescue, once it is established, should take responsibility for maintaining this system.		To discuss with local union representatives how learning could be shared	DPOD / DCFO	Feb 25		Nov update: Discussion were undertaken on this area at consultation meetings with representative bodies in October. / Options put forward for the professional standards may offer some additional routes for learning points in this area.

Status against overall Recommendation

Complete	9
Ongoing	6
Not Started	0

Progress of additional improvement actions

Complete	13
Ongoing	6
Not Started	3